## Overview
| Mon | Tues | Wed | Thur | Fri | Sat | Sun
Week 9 | Ideation + Learning | Ideation + Learning | Ideation + Learning | Idea Presentations + Finalize idea | White Space Day
Week 10 | Bronze Layer | Bronze Layer | Silver Layer | Silver Layer | Silver Layer
Week 11 | Silver Layer | Silver Layer | Gold Layer | Gold Layer | Gold Layer
Week 12 | Dashboard | Dashboard | Presentation Deck/ Documentation | Presentation Deck/ Documentation | Target Completion of Final Project Technical Implementation | YX Triathlon | YX Triathlon
Week 13 | Presentation Deck/ Documentation | Presentation Deck/ Documentation Syafiq Away | Presentation Deck/ Documentation | Final Project Presentation
NOW

## Daily Tracker
Week | Date Opened | Task | Assigned | Due | Open / Closed | Remarks
Week 9 | 2026-01-15 | Create Fabric Workspace and add contributors | Justin | 2026-01-15 | Closed | Fabric Workspace and contributors added successfully.
Week 9 | 2026-01-16 | Create a new shared workspace for testing | Syafiq | 2026-01-16 | Closed | Created a testing workspace within Fabric.
Week 9 | 2026-01-15 | Create Azure Devops git repo and add contributors | Justin | 2026-01-19 | Closed | Free for 5 users. Need to add Credit Card! Justin Create Azure DevOps repo then YX and Syafiq join as contributors
Week 9 | 2026-01-16 | Checking of Azure DevOps | Yong Xiang | 2026-01-19 | Closed
Week 9 | 2026-01-16 | Initial Data Exploration | Syafiq | 2026-01-20 | Closed | game_team_stats, game_shifts, player_info
Week 9 | 2026-01-16 | Initial Data Exploration | Yong Xiang | 2026-01-20 | Closed | game_skater_stats, game_goalie_stats, team_info
Week 9 | 2026-01-16 | Proposal of the Pipeline Architecture (see sprint log) | Yong Xiang | 2026-01-20 | Closed | Stats Dashboard.pptx
Week 9 | 2026-01-19 | Working On Bronze Layer: Check Formatting | Yong Xiang | 2026-01-21 | Closed | Check format, header, data type, filename
Week 10 | 2026-01-19 | Working On Bronze Layer: Loading of Tables | Syafiq | 2026-01-21 | Closed | Load into bronze lakehouse tables
Week 10 | 2026-01-21 | Update the constants table with data types you are working on | All | 2026-01-21 | Closed
Week 10 | 2026-01-19 | Working On Bronze Layer: Checking of loaded Tables | Justin | 2026-01-21 | Closed | Check if table loaded into bronze lakehouse​
Week 10 | 2026-01-16 | Initial Data Exploration | Justin | 2026-01-22 | Closed | game_plays, game_plays_players, game - blocker: calculated wrong no. of duplicates - need to revise - blocker: referential integrity check method research - blocker: uncertain on how to deal with null/na values
Week 10 | 2026-01-21 | Orchestrate in Bronze to Silver | Yong Xiang | 2026-01-22 | Closed | Pending Justin's notebook
Week 10 | 2026-01-21 | Each member clean their own data and load into staging notebook | Yong Xiang | 2026-01-23 | Closed
Week 10 | 2026-01-21 | data quality check notebook | Yong Xiang | 2026-01-23 | Closed | WIP
Week 10 | 2026-01-21 | Each member clean their own data and load into staging notebook | Syafiq | 2026-01-23 | Closed | Double check unclean tables. Then proceed to clean.
Week 10 | 2026-01-21 | data quality check notebook | Syafiq | 2026-01-25 | Closed | Refer to YX notebook
Week 10 | 2026-01-21 | Each member clean their own data and load into staging notebook | Justin | 2026-01-26 | Closed
Week 10 | 2026-01-21 | Checking of loading into bronze staging | Justin | 2026-01-26 | Closed | WIP
Week 10 | 2026-01-21 | data quality check notebook | Justin | 2026-01-26 | Closed | Refer to YX notebook
Week 10 | 2026-01-21 | load into silver warehouse notebook | Syafiq | 2026-01-26 | Closed
Week 10 | 2026-01-21 | move file to processed folder notebook | Yong Xiang | 2026-01-27 | Closed | not required anymore - filed moved to processed at bronze layer
Week 10 | 2026-01-21 | orchestrate tasks between notebooks | Yong Xiang | 2026-01-27 | Closed | WIP. Needs data quality check notebook
Week 10 | 2026-01-21 | check if table loaded into silver tables notebook | Syafiq | 2026-01-27 | Closed | exec_end_time now shows the execution end time through the log. Check with DDC.
Week 11 | 2026-01-28 | - aggregations and loading into silver staging tables notebook | Yong Xiang | 2026-02-02 | Closed | game_goalie_stats, game_skater_stats, team_info, player_info
Week 11 | 2026-01-28 | - data quality check notebook | Justin | 2026-02-02 | Closed
Week 11 | 2026-01-28 | - check if loaded into gold warehouse notebook | Syafiq | 2026-02-02 | Closed
Week 11 | 2026-01-28 | - orchestrate tasks between notebooks | Yong Xiang | 2026-02-02 | Closed | wait for aggregation and data quality notebook
Week 11 | 2026-01-29 | Find which column for primary key, if not, can consider composite key instead. | All | 2026-02-02 | Closed
Week 11 | 2026-01-29 | Use bronze table and connect to powerBI see if it affects anything | Justin | 2026-02-10 | Closed | Can use staging table to test.
Week 11 | 2026-01-29 | Start Overall Documentation Format | Justin | 2026-02-02 | Closed
Week 12 | 2026-02-02 | Implement Incremental load in Silver Layer | Yong Xiang | 2026-02-05 | Closed
Week 12 | 2026-02-03 | Input first draft writeup for documentation for respective assigned parts | All | 2026-02-05 | Closed | Monday
Week 12 | 2026-02-04 | dashboard - insights | Justin | 2026-02-06 | Closed | Before Lunch today
Week 12 | 2026-02-04 | dashboard - team view | Yong Xiang | 2026-02-06 | Closed | After finish commiting the logging in the Gold Layer. Optional
Week 12 | 2026-02-03 | start on slides | Syafiq | 2026-02-09 | Closed | Slides by 2PM today
Week 12 | 2026-02-04 | dashboard - make it nice | Syafiq | 2026-02-09 | Closed
Week 12 | 2026-02-06 | Update Read-Me in Azure Dev ops | All | 2026-02-11 | Closed | When we got time.

## Product_Sprint Log
Milestone | Tasks | Requirements | Expected Output
Ideation | Select Idea | Prepared presentations on findings | Final idea selected
Setup | Workspace permissions | Fabric trial activation and permissions setup in Fabric | All to be able to access same workspace and create items
Setup | Git repository connections to Fabric workspace | Azure devops setup | Items in Fabric to be version controlled in git
Setup | Git contributor access | Azure devops permissions setup | All to be able to commit to and pull from the git repo
Data Architecture Plan | Look at the idea and break down the data pipeline into steps | Idea finalized and entire tech stack confirmed | Detailed steps and expected output in Bronze, Silver, Gold layers and Dashboard Milestones
Bronze Layer | - check format and load notebook - check if table loaded into bronze tables notebook - orchestrate tasks between notebooks | Data architecture plan | Notebooks and pipeline committed into main branch
Silver Layer | - data cleaning and loading into staging tables notebook - check if table loaded into bronze staging tables notebook - data quality check notebook - load into silver warehouse notebook - check if table loaded into silver tables notebook - move file to processed folder notebook - orchestrate tasks between notebooks | Exploratory Data analysis completed. Data architecture plan and bronze layer finalized | Notebooks and pipeline committed into main branch
Gold Layer | - aggregations and loading into silver staging tables notebook - data quality check notebook - check if loaded into gold warehouse notebook - orchestrate tasks between notebooks | Data architecture plan and silver layer finalized | Notebooks and pipeline committed into main branch
Dashboard | - create dashboard of aggregated stats and filters | Gold layer finalized | Dashboard committed into main branch
Project Documentation | - documentation of decisions for each step of the pipeline | Project documentation should be completed as we progress through the milestones | Project documentation document completed and finalized
Presentation Deck | - presentation deck (5-7mins each) | Technical Implementation completed | Powerpoint deck completed and finalized

## Meeting Log
16/1 | YX | Justin | Syafiq
Project Decision: | game_skater_stats | game_plays | game_team_stats
Yong Xiang | game_goalie_stats | game_plays_players | game_shifts
Stretch Goal: can link to score positioning as well as the player scores | team_info | game | player_info
Player scores from which x and y axis
Do individual Data Exploration
Get the main pipeline working
Deciding which columns can be used for the problem statement
Bronze to SIlver: Data Cleaning and rectify anomalies
Silver: Aggregating using notebook for Gold Layer
SIlver to Gold: Business Ready data
Do whatever work in your workspace first then migrate into the Main NHL workspace
Split tables up for data cleaning
Shared workspace for all files testing - Proper naming
No commit, work not done
21/01 | YX | JUSTIN | SYAFIQ
Silver Layer assignment | Orchestrate in Bronze to SIlver | Each member clean their own data and load into staging notebook | Each member clean their own data and load into staging notebook
naming_convention using camel case | Each member clean their own data and load into staging notebook | Checking of loading into bronze staging | data quality check notebook
naming convention according to PEP8 | data quality check notebook | data quality check notebook | load into silver warehouse notebook
| move file to processed folder notebook |  | check if table loaded into silver tables notebook
orchestrate tasks between notebooks
29/01
Find which column for primary key, if not, can consider composite key instead. | YX | Justin | Syafiq
Remember to do documentation and powerpoint slides. Document work done. | game_skater_stats | game_plays | game_team_stats
Use bronze table and connect to powerBI see if it affects anything | game_goalie_stats | game_plays_players | game_shifts
| team_info | game | player_info
Unable to run more than 4 - 5 spark nbs which then lead to capacity error
Implement retry logic inside the pipeline
Write to execute end time for silver load
write to log
save log
gold is a warehouse so we need to create a check load function
game_skater, game_goalie, team_info
confirm gold layer then create semantic model
no additional aggregations in Gold Layer
additional measures do in PowerBI
Test what we can do to the semantic model that can cause it to break.
Severity or to look past any checks being done in gold layer.
If working on powerBI let team know your start and stop!
Share about Scrum tasks and processes.
What to improve? technical and scrum process.
Instead of BI we use screenshots in the PowerPoint
Consider opening report before the presentation and present after the presentation
Documentation

## _data validation (hidden)
Week 9 | Syafiq | Open | 2026-01-15
Week 10 | Justin | Closed | 2026-01-16
Week 11 | Yong Xiang |  | 2026-01-17
Week 12 | All |  | 2026-01-18
Week 13 |  |  | 2026-01-19
2026-01-20
2026-01-21
2026-01-22
2026-01-23
2026-01-24
2026-01-25
2026-01-26
2026-01-27
2026-01-28
2026-01-29
2026-01-30
2026-01-31
2026-02-01
2026-02-02
2026-02-03
2026-02-04
2026-02-05
2026-02-06
2026-02-07
2026-02-08
2026-02-09
2026-02-10
2026-02-11
2026-02-12